Find the critical path and total duration to complete the project.

|  |  |  |
| --- | --- | --- |
| **Activity** | **Predecessor** | **Duration in months** |
| A | - | 2 |
| B | - | 5 |
| C | - | 4 |
| D | B | 5 |
| E | A | 7 |
| F | A | 3 |
| G | B | 3 |
| H | C,D | 6 |
| I | C,D | 2 |
| J | E | 5 |
| K | F,G,H | 4 |
| L | F,G,H | 3 |
| M | I | 12 |
| N | J,K | 8 |